Table of Contents

# CSAT Survey Invitation Email — Plan of Action

Setting up the invitation template and the survey link Environment: adcomsolutionsdev · Version 1.1 — implemented

Status: built and verified. The invitation now follows the same pattern as the existing case survey email and links to the Service Portal. Outbound email remains disabled, so nothing is delivered yet. Sections 1 and 2 record why the change was needed; section 3 records what was built.

## 1. Why this is needed

Surveys raised from the CSAT portal are being picked up by a notification that was written for case-triggered surveys. The result is a broken invitation.

Evidence from the instance:

| Finding | Detail |
| --- | --- |
| Notification firing today | Survey User Invite v2- Manually Created (asmt_assessment_instance, generation type engine) |
| Its condition | metric_type.name = Closed Case Survey and state CHANGES TO ready — which portal surveys satisfy |
| Subject produced | Survey for case- , Site — ${task_id.number} and ${task_id.location} are empty |
| Survey link produced | None |

The missing link is the important part. The body calls the mail script asmt_assessment_instance_script_for_partners, which begins:

var partner = new GlideRecord('customer_account');
partner.addQuery('sys_id', current.task_id.company);
partner.query();
if (partner.next()) {          // never true for a portal survey
    ...
    template.print(html);      // so the link is never printed
}

Portal-raised surveys have no task_id, so the query returns nothing and the link is never written into the email. A recipient would receive a message with a malformed subject and no way to reach the survey.

The stock notification that does contain a working link — Survey Invitation — is currently inactive.

### Confirmed: the link mechanism itself works

Tested against a real portal-created survey instance:

instance:  8e92ec112b2a0f10efa0f95ed891bf13
task_id:   (empty)
url:       https://adcomsolutionsdev.service-now.com/nav_to.do?uri=%2Fassessment_take2.do
           %3Fsysparm_assessable_type=<metric_type>%26sysparm_assessable_sysid=<instance>
linkHtml:  <a href="...">Take me to the Survey</a>

AssessmentUtils().getInstanceLinkHTML(current) needs only the instance, not a case. It is the correct building block.

## 2. Decisions taken

Link destination: Service Portal. Recipients are customer contacts, so the invitation links to /csat?id=take_survey&instance_id=<sys_id> rather than the platform UI. Verified: opening the link as the survey owner loads the survey; opening it as anyone else is correctly refused. The link now lands straight on the first question — see the survey landing page note in the technical design.

Pattern: mirrors the existing case invitation. Same body structure, same covering wording, and the same sender-resolution approach, so the two emails read consistently.

Sender: resolved from the survey.from.mail property using the account on the CSAT request, falling back to support@noc-portal.com — the same rule the case email uses.

Still to confirm with the business: whether a due date should be quoted, and whether branding or a logo is required.

## 3. What was built

Deployed by scripts/deploy-csat-email-template.js, which is idempotent and safe to re-run.

| Artifact | Purpose |
| --- | --- |
| Mail script csat_survey_portal_from | Resolves sender and reply-to from the CSAT request’s account |
| Mail script csat_survey_portal_link | Prints the Service Portal survey link, with a copyable fallback |
| Notification CSAT Survey Invitation | The invitation itself, scoped to portal-raised surveys |
| Condition changes on three existing notifications | Stops them producing a second, broken email |

### Phase 1 — Stop the wrong email (done first)

Three active notifications would otherwise also fire. Each was narrowed, without changing how it behaves for the surveys it was written for.

The obvious guard does not work for all of them. Adding trigger_table != u_x_csat_survey_request only helps for event-based notifications, which are evaluated when the queued event is processed — by which time the portal has stamped the trigger table onto the instance.

Survey User Invite v2- Manually Created is record-based (generation_type = engine), so it is evaluated the instant the instance is inserted, before the trigger table is set. The guard was always true and it kept firing. It is now excluded with task_id IS NOT EMPTY instead — portal surveys have no task, and that notification renders ${task_id.number} in its subject and uses task_id.company to build its link, so without a task it could only ever produce a broken email anyway.

| Notification | Type | Guard applied |
| --- | --- | --- |
| Request survey | event | trigger_table != u_x_csat_survey_request |
| Survey Assigned Notification | event | trigger_table != u_x_csat_survey_request |
| Survey User Invite v2- Manually Created | record | task_id IS NOT EMPTY |

### Phase 2 — Build the link mail script

Create a Mail Script named csat_survey_link.

Option A — platform link, reuses the stock helper:

(function runMailScript(current, template, email, email_action, event) {
    template.print(new AssessmentUtils().getInstanceLinkHTML(current));
})(current, template, email, email_action, event);

Option B — Service Portal link, recommended:

(function runMailScript(current, template, email, email_action, event) {
    var portal = 'csat';
    var base = gs.getProperty('glide.servlet.uri').replace(/\/$/, '');
    var url = base + '/' + portal + '?id=take_survey&instance_id=' + current.getUniqueValue();

    template.print('<p><a href="' + url + '" ' +
        'style="background:#0b5cab;color:#ffffff;padding:12px 22px;' +
        'border-radius:4px;text-decoration:none;display:inline-block;">' +
        'Take the survey</a></p>');
    template.print('<p style="font-size:12px;color:#666;">' +
        'If the button does not work, copy this link:<br/>' + url + '</p>');
})(current, template, email, email_action, event);

The plain-text fallback matters — many corporate mail clients strip styled buttons.

### Phase 3 — Build the invitation notification

Create a Notification on asmt_assessment_instance:

| Field | Value |
| --- | --- |
| Name | CSAT Survey Invitation |
| Table | asmt_assessment_instance |
| Send when | Event is fired |
| Event name | assign.send_survey |
| Generation type | event |
| Users | user (recipient field) |
| Condition | Trigger table is u_x_csat_survey_request |
| Subject | ${metric_type} — we would value your feedback |

Body:

<p>Hi ${user.first_name},</p>

<p>Thank you for working with us. We would appreciate a few minutes of your
time to tell us how we are doing.</p>

<p>The survey takes 1–3 minutes and your answers go directly to the team
supporting your account.</p>

${mail_script:csat_survey_link}

<p>Thank you,<br/>The Customer Success Team</p>

generation_type must be event. The default value engine causes the notification engine to ignore gs.eventQueue events entirely — the event is marked processed and no email is ever produced. This has already caught us once on the submission notifications.

### Phase 4 — Confirm which event fires

Portal surveys are created with an empty source record, so the platform’s Dispatch Survey event (Non triggered) rule raises assign.send_survey. That is the event to listen on.

Both platform dispatch rules require metric_type.notify_user = true. Confirm this is ticked on each survey definition that will be used, otherwise the portal falls back to raising the event itself through CSATSurveyNotification.notifyAssigned().

### Phase 5 — Tested with delivery off

Outbound email is disabled, so everything was written to sys_email without being sent. Verified on adcomsolutionsdev:

Recipient: American Bank Notifications (security@ambk.com)
Emails generated for this recipient: 1
   Closed Case Survey - we would value your feedback
Link: https://adcomsolutionsdev.service-now.com/csat?id=take_survey
      &instance_id=698ba85d2be2cf1007a3fa95b891bfa4

| Check | Result |
| --- | --- |
| Exactly one invitation per recipient | Yes — the duplicate no longer fires |
| Subject renders the survey name | Closed Case Survey - we would value your feedback |
| No empty placeholders | Confirmed |
| Survey link present | Yes, Service Portal |
| Link opens the survey for its owner | Verified — lands on the first question |
| Link refused for anyone else | Verified — “not authorized or the record is not valid” |

### Phase 6 — Enable delivery

- Review anything already queued in sys_email so switching on does not release a backlog

- Set glide.email.smtp.active = true

- Send to one internal recipient and confirm receipt and the link

- Then send to a genuine customer contact

## 4. Prerequisites still outstanding

These block a live send regardless of the email template:

| Item | Status |
| --- | --- |
| Outbound email enabled | Off |
| Closed Case Survey | Published, 1 question |
| Managed Network Services Survey - Manual | Draft, 0 questions |
| Managed Network Services Survey - Automatic | Draft, 0 questions |
| Primary Billing Contact populated | 1 company only |

A survey with one question will produce a very thin invitation. Content should be reviewed alongside the email wording.

## 5. Sequence and dependencies

Phase 1  Exclude portal surveys from the case notification   ← do first
Phase 2  Create the csat_survey_link mail script
Phase 3  Create the CSAT Survey Invitation notification
Phase 4  Confirm notify_user on each survey definition
Phase 5  Test with email still disabled
Phase 6  Enable delivery, pilot, then roll out

Phases 2 and 3 can be done together. Phase 1 must precede Phase 6 or recipients receive two emails.

## 6. Risks

| Risk | Mitigation |
| --- | --- |
| Duplicate invitations | Phase 1 excludes portal surveys from the case notification; verify only one sys_email row per recipient in Phase 5 |
| Notification silently produces nothing | Set generation_type = event; confirm a sys_email record appears in Phase 5 |
| Enabling SMTP releases a backlog | Review the queue before switching on |
| Link resolves for the wrong person | Assessment instances are per-user; confirm in Phase 5 by opening the link |
| Wrong sender identity | Agree sender name and reply-to before Phase 6 |

## 7. Rollback

Each phase is independently reversible.

| To undo | Action |
| --- | --- |
| The new invitation | Set CSAT Survey Invitation to inactive |
| The Phase 1 exclusion | Remove the trigger table condition |
| Delivery | Set glide.email.smtp.active = false |

No data model or portal changes are involved, so nothing needs redeploying.

## 8. What we still need from you

- Approve the wording — subject line and covering text as built

- Confirm the sender mapping covers the accounts you will survey, since anything unmapped falls back to support@noc-portal.com

- Enable outbound email once the existing queue has been reviewed

- Owner and date for publishing the two Draft surveys

The build is captured in the update set CSAT Survey Portal - Invitation email for promotion, consistent with the rest of the solution.